## Sprint Planning
The first sprint's goal for project is to develop the basic structure for the application like (sign up , login , viewing home page for application which contains most of resaurants).
# | Epic | User Story | Team Capacity | team capacity (In hours) | Assign To
1 | Create Account | As a customer , I want to create an account so that I can login to request an order from any restaurant. | 2 | 10
There are 3 types of user (customer,administrator for each resturant and delivery person).
2 | View Restaurants | As a customer , I want to view restaurants so that I can choose a restaurant to request an order. | 3 | 7
After login for customer he will see most of restaurants in the home page.
3 | Search Restaurants | As a customer , I want to search restaurants so that I can find a specific restaurant to request an order from it. | 1 | 8
there will be an icon for search to search for meal or restaurant.
4 | View Menu | As a customer , I want to view menu so that I can choose a meal to request an order from the restaurant. | 2 | 7
there will be a listview for menu of each restaurant.
5 | Add to Cart | As a customer , I want to add to cart so that I can add more than one order to order them fom different restaurants and choose a payment method and choose my current address. | 1 | 8
there will be an icon for cart to add meals to his cart.
6 | Purchase | As a customer , I want to purchase so that I can choose a payment method. | 2 | 10
there will be a listview for each payment methods.
7 | Restaurant views order | As a customer , I want to see the views of restaurant purchase so that I can choose a restaurant from the recommended restaurants. | 1 | 10
there will be an icon to view the rate for each restaurant.
8 | Restaurant marks order as delivered | As a customer , I want to see the status of an order which I ordered so that I can know if I can complete the request or I can change the satus of request as cancelled for example. | 1 | 18
there will be changeable text to view the status of an order.
|  |  | Total estimated team capacity | 78 hour/sprint