## Task Board & Burn Down Chart
TASK BOARD
EPIC | TO DO | IN PROGRESS | TESTING | DONE
Create Account | Checking duplicated accounts from database. | sign up using different accounts like(google,facebook). | the design of sign up and login page. | Sign up and login page design.
| sending verfication email to user to verify his email. | ----- | ----- | -----
View Restaurants | creating listview to collect all restaurants | ----- | testing moving from login page to | creating home page for application
Search Restaurants | connecting database of restaurants with the search icon | competing search algorithm | checking the second page after pressing in search icon | choosing the place and design of search icon
View Menu | connecting database of restaurants menu with the design | ----- | ----- | creating the design of menu for each restauran
Add to Cart | connecting database of restaurants with the cart | create listview for cart | checking the second page after pressing in cart icon | choosing the place and design of cart icon and putting it in different places in the application
Purchase | connecting database of restaurants with the payment methods | ----- | checking the payment methods after pressing in payment button | choosing payment methods and connecting them with the application
Restaurant views order | creating the design of rating to each restaurant | ----- | the design of restaurants views | the design of choosing the rate for the restaurant and the total number of users who rated
Restaurant marks order as delivered | connecting database of restaurants with the status of an order | ----- | the design of the status of an order | the design of the status of an order
Add to cart
|  | Task name | estimated Duration | Actual Duration | estimated Remaining Days | Actual Remaining Days
|  | connecting database of restaurants with the cart | 1 | 1 | 6 | 7
|  | create listview for cart | 2 | 2 | 4 | 5
|  | checking the second page after pressing in cart icon | 2 | 3 | 6 | 7
|  | choosing the place and design of cart icon and putting it in different places in the application | 1 | 1 | 5 | 7
0
1
2
3
4
5